## Variables
Windows 10 Builds | Device Counts
1507 | 0
1511 | 0
1607 | 12
1703 | 429
1709 | 30937
1803 | 20
1809 | 5617
1903 | 5
1909
2002
2009
2103
2109
WaaS IPU Start | 2019-10-14
WaaS IPU End | 2020-02-28
Projections
Starting Count | 31398
Timeframe (Weeks) | 19
Projected Pace | 1652.5263
IPU 25% | 23548.5
IPU 50% | 15699
IPU 75% | 7849.5
IPU 100% | 0
Target Build | 1809

## Worksheet
Year | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2022
Month | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | May
Day | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30
Remaining Weeks | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
Remaining Months | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -2 | -2 | -2 | -2 | -3 | -3 | -3 | -3 | -4 | -4 | -4 | -4 | -4 | -5 | -5 | -5 | -5 | -6 | -6 | -6 | -6 | -6 | -7 | -7 | -7 | -7 | -8 | -8 | -8 | -8 | -9 | -9 | -9 | -9 | -9 | -10 | -10 | -10 | -10 | -11 | -11 | -11 | -11 | -12 | -12 | -12 | -12 | -13 | -13 | -13 | -13 | -13 | -14 | -14 | -14 | -14 | -15 | -15 | -15 | -15 | -15 | -16 | -16 | -16 | -16 | -17 | -17 | -17 | -17 | -18 | -18 | -18 | -18 | -18 | -19 | -19 | -19 | -19 | -20 | -20 | -20 | -20 | -21 | -21 | -21 | -21 | -21 | -22 | -22 | -22 | -22 | -23 | -23 | -23 | -23 | -23 | -24 | -24 | -24 | -24 | -25 | -25 | -25 | -25 | -26 | -26 | -26 | -26 | -27 | -27 | -27 | -27 | -27
Actual Machine Counts
Windows 10 Build 1507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1507
Windows 10 Build 1511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1511
Windows 10 Build 1607 | 12 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 1607
Windows 10 Build 1703 | 429 | 388 | 380 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 338 | 1703
Windows 10 Build 1709 | 30937 | 30740 | 30660 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 30536 | 1709
Windows 10 Build 1803 | 20 | 21 | 21 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1803
Windows 10 Build 1809 | 5617 | 6474 | 6706 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 7079 | 1809
Windows 10 Build 1903 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1903
Windows 10 Build 1909 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1909
Total [Pre-1809] | 31398 | 31160 | 31072 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908 | 30908
Total [Post-1809] | 5622 | 6481 | 6714 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086 | 7086
Weekly Change [Pre-1809] |  | -238 | -88 | -164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly Change [Post-1809] |  | 859 | 233 | 372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Change [Pre-1809] |  | -238 | -326 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490 | -490
Running Change [Post-1809] |  | 859 | 1092 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464 | 1464
Average Weekly Change [Pre-1809] |  | -238 | -163 | -163.3333 | -122.5 | -98 | -81.6667 | -70 | -61.25 | -54.4444 | -49 | -44.5455 | -40.8333 | -37.6923 | -35 | -32.6667 | -30.625 | -28.8235 | -27.2222 | -25.7895 | -24.5 | -23.3333 | -22.2727 | -21.3043 | -20.4167 | -19.6 | -18.8462 | -18.1481 | -17.5 | -16.8966 | -16.3333 | -15.8065 | -15.3125 | -14.8485 | -14.4118 | -14 | -13.6111 | -13.2432 | -12.8947 | -12.5641 | -12.25 | -11.9512 | -11.6667 | -11.3953 | -11.1364 | -10.8889 | -10.6522 | -10.4255 | -10.2083 | -10 | -9.8 | -9.6078 | -9.4231 | -9.2453 | -9.0741 | -8.9091 | -8.75 | -8.5965 | -8.4483 | -8.3051 | -8.1667 | -8.0328 | -7.9032 | -7.7778 | -7.6562 | -7.5385 | -7.4242 | -7.3134 | -7.2059 | -7.1014 | -7 | -6.9014 | -6.8056 | -6.7123 | -6.6216 | -6.5333 | -6.4474 | -6.3636 | -6.2821 | -6.2025 | -6.125 | -6.0494 | -5.9756 | -5.9036 | -5.8333 | -5.7647 | -5.6977 | -5.6322 | -5.5682 | -5.5056 | -5.4444 | -5.3846 | -5.3261 | -5.2688 | -5.2128 | -5.1579 | -5.1042 | -5.0515 | -5 | -4.9495 | -4.9 | -4.8515 | -4.8039 | -4.7573 | -4.7115 | -4.6667 | -4.6226 | -4.5794 | -4.537 | -4.4954 | -4.4545 | -4.4144 | -4.375 | -4.3363 | -4.2982 | -4.2609 | -4.2241 | -4.188 | -4.1525 | -4.1176 | -4.0833 | -4.0496 | -4.0164 | -3.9837 | -3.9516 | -3.92 | -3.8889 | -3.8583 | -3.8281 | -3.7984 | -3.7692 | -3.7405 | -3.7121 | -3.6842 | -3.6567 | -3.6296 | -3.6029 | -3.5766
Average Weekly Change [Post-1809] |  | 859 | 546 | 488 | 366 | 292.8 | 244 | 209.1429 | 183 | 162.6667 | 146.4 | 133.0909 | 122 | 112.6154 | 104.5714 | 97.6 | 91.5 | 86.1176 | 81.3333 | 77.0526 | 73.2 | 69.7143 | 66.5455 | 63.6522 | 61 | 58.56 | 56.3077 | 54.2222 | 52.2857 | 50.4828 | 48.8 | 47.2258 | 45.75 | 44.3636 | 43.0588 | 41.8286 | 40.6667 | 39.5676 | 38.5263 | 37.5385 | 36.6 | 35.7073 | 34.8571 | 34.0465 | 33.2727 | 32.5333 | 31.8261 | 31.1489 | 30.5 | 29.8776 | 29.28 | 28.7059 | 28.1538 | 27.6226 | 27.1111 | 26.6182 | 26.1429 | 25.6842 | 25.2414 | 24.8136 | 24.4 | 24 | 23.6129 | 23.2381 | 22.875 | 22.5231 | 22.1818 | 21.8507 | 21.5294 | 21.2174 | 20.9143 | 20.6197 | 20.3333 | 20.0548 | 19.7838 | 19.52 | 19.2632 | 19.013 | 18.7692 | 18.5316 | 18.3 | 18.0741 | 17.8537 | 17.6386 | 17.4286 | 17.2235 | 17.0233 | 16.8276 | 16.6364 | 16.4494 | 16.2667 | 16.0879 | 15.913 | 15.7419 | 15.5745 | 15.4105 | 15.25 | 15.0928 | 14.9388 | 14.7879 | 14.64 | 14.495 | 14.3529 | 14.2136 | 14.0769 | 13.9429 | 13.8113 | 13.6822 | 13.5556 | 13.4312 | 13.3091 | 13.1892 | 13.0714 | 12.9558 | 12.8421 | 12.7304 | 12.6207 | 12.5128 | 12.4068 | 12.3025 | 12.2 | 12.0992 | 12 | 11.9024 | 11.8065 | 11.712 | 11.619 | 11.5276 | 11.4375 | 11.3488 | 11.2615 | 11.1756 | 11.0909 | 11.0075 | 10.9254 | 10.8444 | 10.7647 | 10.6861
Migration Progress [Percentage Complete]
Pre-1809 Reduction (Projecct Progress) | 0 | 0.758% | 1.038% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561% | 1.561%
Total Population (All Windows 10 Builds) | 37020 | 37641 | 37786 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994 | 37994
Upgraded Windows 10 Percentage of Population | 15.19% | 17.22% | 17.77% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65% | 18.65%
Migration Progress
Projected Pre-1809 Counts | 31398 | 29745.4737 | 28092.9474 | 26440.4211 | 24787.8947 | 23135.3684 | 21482.8421 | 19830.3158 | 18177.7895 | 16525.2632 | 14872.7368 | 13220.2105 | 11567.6842 | 9915.1579 | 8262.6316 | 6610.1053 | 4957.5789 | 3305.0526 | 1652.5263 | 5.9117e-12 | -1652.5263 | -3305.0526 | -4957.5789 | -6610.1053 | -8262.6316 | -9915.1579 | -11567.6842 | -13220.2105 | -14872.7368 | -16525.2632 | -18177.7895 | -19830.3158 | -21482.8421 | -23135.3684 | -24787.8947 | -26440.4211 | -28092.9474 | -29745.4737 | -31398 | -33050.5263 | -34703.0526 | -36355.5789 | -38008.1053 | -39660.6316 | -41313.1579 | -42965.6842 | -44618.2105 | -46270.7368 | -47923.2632 | -49575.7895 | -51228.3158 | -52880.8421 | -54533.3684 | -56185.8947 | -57838.4211 | -59490.9474 | -61143.4737 | -62796 | -64448.5263 | -66101.0526 | -67753.5789 | -69406.1053 | -71058.6316 | -72711.1579 | -74363.6842 | -76016.2105 | -77668.7368 | -79321.2632 | -80973.7895 | -82626.3158 | -84278.8421 | -85931.3684 | -87583.8947 | -89236.4211 | -90888.9474 | -92541.4737 | -94194 | -95846.5263 | -97499.0526 | -99151.5789 | -100804.1053 | -102456.6316 | -104109.1579 | -105761.6842 | -107414.2105 | -109066.7368 | -110719.2632 | -112371.7895 | -114024.3158 | -115676.8421 | -117329.3684 | -118981.8947 | -120634.4211 | -122286.9474 | -123939.4737 | -125592 | -127244.5263 | -128897.0526 | -130549.5789 | -132202.1053 | -133854.6316 | -135507.1579 | -137159.6842 | -138812.2105 | -140464.7368 | -142117.2632 | -143769.7895 | -145422.3158 | -147074.8421 | -148727.3684 | -150379.8947 | -152032.4211 | -153684.9474 | -155337.4737 | -156990 | -158642.5263 | -160295.0526 | -161947.5789 | -163600.1053 | -165252.6316 | -166905.1579 | -168557.6842 | -170210.2105 | -171862.7368 | -173515.2632 | -175167.7895 | -176820.3158 | -178472.8421 | -180125.3684 | -181777.8947 | -183430.4211 | -185082.9474 | -186735.4737 | -188388 | -190040.5263 | -191693.0526 | -193345.5789 | -194998.1053
Running Comparison | 0 | -1414.5263 | -2979.0526 | -4467.5789 | -6120.1053 | -7772.6316 | -9425.1579 | -11077.6842 | -12730.2105 | -14382.7368 | -16035.2632 | -17687.7895 | -19340.3158 | -20992.8421 | -22645.3684 | -24297.8947 | -25950.4211 | -27602.9474 | -29255.4737 | -30908 | -32560.5263 | -34213.0526 | -35865.5789 | -37518.1053 | -39170.6316 | -40823.1579 | -42475.6842 | -44128.2105 | -45780.7368 | -47433.2632 | -49085.7895 | -50738.3158 | -52390.8421 | -54043.3684 | -55695.8947 | -57348.4211 | -59000.9474 | -60653.4737 | -62306 | -63958.5263 | -65611.0526 | -67263.5789 | -68916.1053 | -70568.6316 | -72221.1579 | -73873.6842 | -75526.2105 | -77178.7368 | -78831.2632 | -80483.7895 | -82136.3158 | -83788.8421 | -85441.3684 | -87093.8947 | -88746.4211 | -90398.9474 | -92051.4737 | -93704 | -95356.5263 | -97009.0526 | -98661.5789 | -100314.1053 | -101966.6316 | -103619.1579 | -105271.6842 | -106924.2105 | -108576.7368 | -110229.2632 | -111881.7895 | -113534.3158 | -115186.8421 | -116839.3684 | -118491.8947 | -120144.4211 | -121796.9474 | -123449.4737 | -125102 | -126754.5263 | -128407.0526 | -130059.5789 | -131712.1053 | -133364.6316 | -135017.1579 | -136669.6842 | -138322.2105 | -139974.7368 | -141627.2632 | -143279.7895 | -144932.3158 | -146584.8421 | -148237.3684 | -149889.8947 | -151542.4211 | -153194.9474 | -154847.4737 | -156500 | -158152.5263 | -159805.0526 | -161457.5789 | -163110.1053 | -164762.6316 | -166415.1579 | -168067.6842 | -169720.2105 | -171372.7368 | -173025.2632 | -174677.7895 | -176330.3158 | -177982.8421 | -179635.3684 | -181287.8947 | -182940.4211 | -184592.9474 | -186245.4737 | -187898 | -189550.5263 | -191203.0526 | -192855.5789 | -194508.1053 | -196160.6316 | -197813.1579 | -199465.6842 | -201118.2105 | -202770.7368 | -204423.2632 | -206075.7895 | -207728.3158 | -209380.8421 | -211033.3684 | -212685.8947 | -214338.4211 | -215990.9474 | -217643.4737 | -219296 | -220948.5263 | -222601.0526 | -224253.5789 | -225906.1053
Weeks into the Project |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137
Ahead/Behind Schedule |  | -0.85598 | -1.8027 | -2.7035 | -3.7035 | -4.7035 | -5.7035 | -6.7035 | -7.7035 | -8.7035 | -9.7035 | -10.7035 | -11.7035 | -12.7035 | -13.7035 | -14.7035 | -15.7035 | -16.7035 | -17.7035 | -18.7035 | -19.7035 | -20.7035 | -21.7035 | -22.7035 | -23.7035 | -24.7035 | -25.7035 | -26.7035 | -27.7035 | -28.7035 | -29.7035 | -30.7035 | -31.7035 | -32.7035 | -33.7035 | -34.7035 | -35.7035 | -36.7035 | -37.7035 | -38.7035 | -39.7035 | -40.7035 | -41.7035 | -42.7035 | -43.7035 | -44.7035 | -45.7035 | -46.7035 | -47.7035 | -48.7035 | -49.7035 | -50.7035 | -51.7035 | -52.7035 | -53.7035 | -54.7035 | -55.7035 | -56.7035 | -57.7035 | -58.7035 | -59.7035 | -60.7035 | -61.7035 | -62.7035 | -63.7035 | -64.7035 | -65.7035 | -66.7035 | -67.7035 | -68.7035 | -69.7035 | -70.7035 | -71.7035 | -72.7035 | -73.7035 | -74.7035 | -75.7035 | -76.7035 | -77.7035 | -78.7035 | -79.7035 | -80.7035 | -81.7035 | -82.7035 | -83.7035 | -84.7035 | -85.7035 | -86.7035 | -87.7035 | -88.7035 | -89.7035 | -90.7035 | -91.7035 | -92.7035 | -93.7035 | -94.7035 | -95.7035 | -96.7035 | -97.7035 | -98.7035 | -99.7035 | -100.7035 | -101.7035 | -102.7035 | -103.7035 | -104.7035 | -105.7035 | -106.7035 | -107.7035 | -108.7035 | -109.7035 | -110.7035 | -111.7035 | -112.7035 | -113.7035 | -114.7035 | -115.7035 | -116.7035 | -117.7035 | -118.7035 | -119.7035 | -120.7035 | -121.7035 | -122.7035 | -123.7035 | -124.7035 | -125.7035 | -126.7035 | -127.7035 | -128.7035 | -129.7035 | -130.7035 | -131.7035 | -132.7035 | -133.7035 | -134.7035 | -135.7035 | -136.7035
Forecasts Based on Actual Machine Counts
Monthly Pace Required | 7849.5 | 7790 | 7768 | 10302.6667 | 10302.6667 | 10302.6667 | 10302.6667 | 15454 | 15454 | 15454 | 15454 | 15454 | 30908 | 30908 | 30908 | 30908 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -30908 | -30908 | -30908 | -30908 | -30908 | -15454 | -15454 | -15454 | -15454 | -10302.6667 | -10302.6667 | -10302.6667 | -10302.6667 | -7727 | -7727 | -7727 | -7727 | -7727 | -6181.6 | -6181.6 | -6181.6 | -6181.6 | -5151.3333 | -5151.3333 | -5151.3333 | -5151.3333 | -5151.3333 | -4415.4286 | -4415.4286 | -4415.4286 | -4415.4286 | -3863.5 | -3863.5 | -3863.5 | -3863.5 | -3434.2222 | -3434.2222 | -3434.2222 | -3434.2222 | -3434.2222 | -3090.8 | -3090.8 | -3090.8 | -3090.8 | -2809.8182 | -2809.8182 | -2809.8182 | -2809.8182 | -2575.6667 | -2575.6667 | -2575.6667 | -2575.6667 | -2377.5385 | -2377.5385 | -2377.5385 | -2377.5385 | -2377.5385 | -2207.7143 | -2207.7143 | -2207.7143 | -2207.7143 | -2060.5333 | -2060.5333 | -2060.5333 | -2060.5333 | -2060.5333 | -1931.75 | -1931.75 | -1931.75 | -1931.75 | -1818.1176 | -1818.1176 | -1818.1176 | -1818.1176 | -1717.1111 | -1717.1111 | -1717.1111 | -1717.1111 | -1717.1111 | -1626.7368 | -1626.7368 | -1626.7368 | -1626.7368 | -1545.4 | -1545.4 | -1545.4 | -1545.4 | -1471.8095 | -1471.8095 | -1471.8095 | -1471.8095 | -1471.8095 | -1404.9091 | -1404.9091 | -1404.9091 | -1404.9091 | -1343.8261 | -1343.8261 | -1343.8261 | -1343.8261 | -1343.8261 | -1287.8333 | -1287.8333 | -1287.8333 | -1287.8333 | -1236.32 | -1236.32 | -1236.32 | -1236.32 | -1188.7692 | -1188.7692 | -1188.7692 | -1188.7692 | -1144.7407 | -1144.7407 | -1144.7407 | -1144.7407 | -1144.7407
Weekly Pace Required | 1652.5263 | 1731.1111 | 1827.7647 | 1931.75 | 2060.5333 | 2207.7143 | 2377.5385 | 2575.6667 | 2809.8182 | 3090.8 | 3434.2222 | 3863.5 | 4415.4286 | 5151.3333 | 6181.6 | 7727 | 10302.6667 | 15454 | 30908 | #DIV/0! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
Projected Milestones
Projected Target Date for 25% Complete |  | 2020-05-31 20:49 | 2020-09-15 02:17 | 2020-09-14 09:46 | 2021-01-04 13:02 | 2021-04-26 16:17 | 2021-08-16 19:33 | 2021-12-06 22:48 | 2022-03-29 02:03 | 2022-07-19 05:19 | 2022-11-08 08:34 | 2023-02-28 11:50 | 2023-06-20 15:05 | 2023-10-10 18:21 | 2024-01-30 21:36 | 2024-05-22 00:51 | 2024-09-11 04:07 | 2025-01-01 07:22 | 2025-04-23 10:38 | 2025-08-13 13:53 | 2025-12-03 17:09 | 2026-03-25 20:24 | 2026-07-15 23:39 | 2026-11-05 02:55 | 2027-02-25 06:10 | 2027-06-17 09:26 | 2027-10-07 12:41 | 2028-01-27 15:57 | 2028-05-18 19:12 | 2028-09-07 22:27 | 2028-12-29 01:43 | 2029-04-20 04:58 | 2029-08-10 08:14 | 2029-11-30 11:29 | 2030-03-22 14:45 | 2030-07-12 18:00 | 2030-11-01 21:15 | 2031-02-22 00:31 | 2031-06-14 03:46 | 2031-10-04 07:02 | 2032-01-24 10:17 | 2032-05-15 13:33 | 2032-09-04 16:48 | 2032-12-25 20:03 | 2033-04-16 23:19 | 2033-08-07 02:34 | 2033-11-27 05:50 | 2034-03-19 09:05 | 2034-07-09 12:21 | 2034-10-29 15:36 | 2035-02-18 18:51 | 2035-06-10 22:07 | 2035-10-01 01:22 | 2036-01-21 04:38 | 2036-05-12 07:53 | 2036-09-01 11:09 | 2036-12-22 14:24 | 2037-04-13 17:39 | 2037-08-03 20:55 | 2037-11-24 00:10 | 2038-03-16 03:26 | 2038-07-06 06:41 | 2038-10-26 09:57 | 2039-02-15 13:12 | 2039-06-07 16:27 | 2039-09-27 19:43 | 2040-01-17 22:58 | 2040-05-09 02:14 | 2040-08-29 05:29 | 2040-12-19 08:45 | 2041-04-10 12:00 | 2041-07-31 15:15 | 2041-11-20 18:31 | 2042-03-12 21:46 | 2042-07-03 01:02 | 2042-10-23 04:17 | 2043-02-12 07:33 | 2043-06-04 10:48 | 2043-09-24 14:03 | 2044-01-14 17:19 | 2044-05-05 20:34 | 2044-08-25 23:50 | 2044-12-16 03:05 | 2045-04-07 06:21 | 2045-07-28 09:36 | 2045-11-17 12:51 | 2046-03-09 16:07 | 2046-06-29 19:22 | 2046-10-19 22:38 | 2047-02-09 01:53 | 2047-06-01 05:09 | 2047-09-21 08:24 | 2048-01-11 11:39 | 2048-05-02 14:55 | 2048-08-22 18:10 | 2048-12-12 21:26 | 2049-04-04 00:41 | 2049-07-25 03:57 | 2049-11-14 07:12 | 2050-03-06 10:27 | 2050-06-26 13:43 | 2050-10-16 16:58 | 2051-02-05 20:14 | 2051-05-28 23:29 | 2051-09-18 02:45 | 2052-01-08 06:00 | 2052-04-29 09:15 | 2052-08-19 12:31 | 2052-12-09 15:46 | 2053-03-31 19:02 | 2053-07-21 22:17 | 2053-11-11 01:33 | 2054-03-03 04:48 | 2054-06-23 08:03 | 2054-10-13 11:19 | 2055-02-02 14:34 | 2055-05-25 17:50 | 2055-09-14 21:05 | 2056-01-05 00:21 | 2056-04-26 03:36 | 2056-08-16 06:51 | 2056-12-06 10:07 | 2057-03-28 13:22 | 2057-07-18 16:38 | 2057-11-07 19:53 | 2058-02-27 23:09 | 2058-06-20 02:24 | 2058-10-10 05:39 | 2059-01-30 08:55 | 2059-05-22 12:10 | 2059-09-11 15:26 | 2060-01-01 18:41 | 2060-04-22 21:57 | 2060-08-13 01:12 | 2060-12-03 04:27 | 2061-03-25 07:43 | 2061-07-15 10:58 | 2061-11-04 14:14
Projected Target Date for 50% Complete |  | 2021-01-17 17:39 | 2021-08-18 04:34 | 2021-08-16 19:33 | 2022-03-29 02:03 | 2022-11-08 08:34 | 2023-06-20 15:05 | 2024-01-30 21:36 | 2024-09-11 04:07 | 2025-04-23 10:38 | 2025-12-03 17:09 | 2026-07-15 23:39 | 2027-02-25 06:10 | 2027-10-07 12:41 | 2028-05-18 19:12 | 2028-12-29 01:43 | 2029-08-10 08:14 | 2030-03-22 14:45 | 2030-11-01 21:15 | 2031-06-14 03:46 | 2032-01-24 10:17 | 2032-09-04 16:48 | 2033-04-16 23:19 | 2033-11-27 05:50 | 2034-07-09 12:21 | 2035-02-18 18:51 | 2035-10-01 01:22 | 2036-05-12 07:53 | 2036-12-22 14:24 | 2037-08-03 20:55 | 2038-03-16 03:26 | 2038-10-26 09:57 | 2039-06-07 16:27 | 2040-01-17 22:58 | 2040-08-29 05:29 | 2041-04-10 12:00 | 2041-11-20 18:31 | 2042-07-03 01:02 | 2043-02-12 07:33 | 2043-09-24 14:03 | 2044-05-05 20:34 | 2044-12-16 03:05 | 2045-07-28 09:36 | 2046-03-09 16:07 | 2046-10-19 22:38 | 2047-06-01 05:09 | 2048-01-11 11:39 | 2048-08-22 18:10 | 2049-04-04 00:41 | 2049-11-14 07:12 | 2050-06-26 13:43 | 2051-02-05 20:14 | 2051-09-18 02:45 | 2052-04-29 09:15 | 2052-12-09 15:46 | 2053-07-21 22:17 | 2054-03-03 04:48 | 2054-10-13 11:19 | 2055-05-25 17:50 | 2056-01-05 00:21 | 2056-08-16 06:51 | 2057-03-28 13:22 | 2057-11-07 19:53 | 2058-06-20 02:24 | 2059-01-30 08:55 | 2059-09-11 15:26 | 2060-04-22 21:57 | 2060-12-03 04:27 | 2061-07-15 10:58 | 2062-02-24 17:29 | 2062-10-07 | 2063-05-19 06:31 | 2063-12-29 13:02 | 2064-08-09 19:33 | 2065-03-22 02:03 | 2065-11-01 08:34 | 2066-06-13 15:05 | 2067-01-23 21:36 | 2067-09-05 04:07 | 2068-04-16 10:38 | 2068-11-26 17:09 | 2069-07-08 23:39 | 2070-02-18 06:10 | 2070-09-30 12:41 | 2071-05-12 19:12 | 2071-12-23 01:43 | 2072-08-03 08:14 | 2073-03-15 14:45 | 2073-10-25 21:15 | 2074-06-07 03:46 | 2075-01-17 10:17 | 2075-08-29 16:48 | 2076-04-09 23:19 | 2076-11-20 05:50 | 2077-07-02 12:21 | 2078-02-11 18:51 | 2078-09-24 01:22 | 2079-05-06 07:53 | 2079-12-16 14:24 | 2080-07-27 20:55 | 2081-03-09 03:26 | 2081-10-19 09:57 | 2082-05-31 16:27 | 2083-01-10 22:58 | 2083-08-23 05:29 | 2084-04-03 12:00 | 2084-11-13 18:31 | 2085-06-26 01:02 | 2086-02-05 07:33 | 2086-09-17 14:03 | 2087-04-29 20:34 | 2087-12-10 03:05 | 2088-07-21 09:36 | 2089-03-02 16:07 | 2089-10-12 22:38 | 2090-05-25 05:09 | 2091-01-04 11:39 | 2091-08-16 18:10 | 2092-03-28 00:41 | 2092-11-07 07:12 | 2093-06-19 13:43 | 2094-01-29 20:14 | 2094-09-11 02:45 | 2095-04-23 09:15 | 2095-12-03 15:46 | 2096-07-14 22:17 | 2097-02-24 04:48 | 2097-10-06 11:19 | 2098-05-18 17:50 | 2098-12-29 00:21 | 2099-08-10 06:51 | 2100-03-22 13:22 | 2100-11-01 19:53 | 2101-06-14 02:24 | 2102-01-24 08:55 | 2102-09-05 15:26 | 2103-04-17 21:57 | 2103-11-28 04:27
Projected Target Date for 75% Complete |  | 2021-09-05 14:28 | 2022-07-21 06:51 | 2022-07-19 05:19 | 2023-06-20 15:05 | 2024-05-22 00:51 | 2025-04-23 10:38 | 2026-03-25 20:24 | 2027-02-25 06:10 | 2028-01-27 15:57 | 2028-12-29 01:43 | 2029-11-30 11:29 | 2030-11-01 21:15 | 2031-10-04 07:02 | 2032-09-04 16:48 | 2033-08-07 02:34 | 2034-07-09 12:21 | 2035-06-10 22:07 | 2036-05-12 07:53 | 2037-04-13 17:39 | 2038-03-16 03:26 | 2039-02-15 13:12 | 2040-01-17 22:58 | 2040-12-19 08:45 | 2041-11-20 18:31 | 2042-10-23 04:17 | 2043-09-24 14:03 | 2044-08-25 23:50 | 2045-07-28 09:36 | 2046-06-29 19:22 | 2047-06-01 05:09 | 2048-05-02 14:55 | 2049-04-04 00:41 | 2050-03-06 10:27 | 2051-02-05 20:14 | 2052-01-08 06:00 | 2052-12-09 15:46 | 2053-11-11 01:33 | 2054-10-13 11:19 | 2055-09-14 21:05 | 2056-08-16 06:51 | 2057-07-18 16:38 | 2058-06-20 02:24 | 2059-05-22 12:10 | 2060-04-22 21:57 | 2061-03-25 07:43 | 2062-02-24 17:29 | 2063-01-27 03:15 | 2063-12-29 13:02 | 2064-11-29 22:48 | 2065-11-01 08:34 | 2066-10-03 18:21 | 2067-09-05 04:07 | 2068-08-06 13:53 | 2069-07-08 23:39 | 2070-06-10 09:26 | 2071-05-12 19:12 | 2072-04-13 04:58 | 2073-03-15 14:45 | 2074-02-15 00:31 | 2075-01-17 10:17 | 2075-12-19 20:03 | 2076-11-20 05:50 | 2077-10-22 15:36 | 2078-09-24 01:22 | 2079-08-26 11:09 | 2080-07-27 20:55 | 2081-06-29 06:41 | 2082-05-31 16:27 | 2083-05-03 02:14 | 2084-04-03 12:00 | 2085-03-05 21:46 | 2086-02-05 07:33 | 2087-01-07 17:19 | 2087-12-10 03:05 | 2088-11-10 12:51 | 2089-10-12 22:38 | 2090-09-14 08:24 | 2091-08-16 18:10 | 2092-07-18 03:57 | 2093-06-19 13:43 | 2094-05-21 23:29 | 2095-04-23 09:15 | 2096-03-24 19:02 | 2097-02-24 04:48 | 2098-01-26 14:34 | 2098-12-29 00:21 | 2099-11-30 10:07 | 2100-11-01 19:53 | 2101-10-04 05:39 | 2102-09-05 15:26 | 2103-08-08 01:12 | 2104-07-09 10:58 | 2105-06-10 20:45 | 2106-05-13 06:31 | 2107-04-14 16:17 | 2108-03-16 02:03 | 2109-02-15 11:50 | 2110-01-17 21:36 | 2110-12-20 07:22 | 2111-11-21 17:09 | 2112-10-23 02:55 | 2113-09-24 12:41 | 2114-08-26 22:27 | 2115-07-29 08:14 | 2116-06-29 18:00 | 2117-06-01 03:46 | 2118-05-03 13:33 | 2119-04-04 23:19 | 2120-03-06 09:05 | 2121-02-05 18:51 | 2122-01-08 04:38 | 2122-12-10 14:24 | 2123-11-12 00:10 | 2124-10-13 09:57 | 2125-09-14 19:43 | 2126-08-17 05:29 | 2127-07-19 15:15 | 2128-06-20 01:02 | 2129-05-22 10:48 | 2130-04-23 20:34 | 2131-03-26 06:21 | 2132-02-25 16:07 | 2133-01-27 01:53 | 2133-12-29 11:39 | 2134-11-30 21:26 | 2135-11-02 07:12 | 2136-10-03 16:58 | 2137-09-05 02:45 | 2138-08-07 12:31 | 2139-07-09 22:17 | 2140-06-10 08:03 | 2141-05-12 17:50 | 2142-04-14 03:36 | 2143-03-16 13:22 | 2144-02-15 23:09 | 2145-01-17 08:55 | 2145-12-19 18:41
Projected Target Date for 100% Complete |  | 2022-04-24 11:18 | 2023-06-23 09:08 | 2023-06-20 15:05 | 2024-09-11 04:07 | 2025-12-03 17:09 | 2027-02-25 06:10 | 2028-05-18 19:12 | 2029-08-10 08:14 | 2030-11-01 21:15 | 2032-01-24 10:17 | 2033-04-16 23:19 | 2034-07-09 12:21 | 2035-10-01 01:22 | 2036-12-22 14:24 | 2038-03-16 03:26 | 2039-06-07 16:27 | 2040-08-29 05:29 | 2041-11-20 18:31 | 2043-02-12 07:33 | 2044-05-05 20:34 | 2045-07-28 09:36 | 2046-10-19 22:38 | 2048-01-11 11:39 | 2049-04-04 00:41 | 2050-06-26 13:43 | 2051-09-18 02:45 | 2052-12-09 15:46 | 2054-03-03 04:48 | 2055-05-25 17:50 | 2056-08-16 06:51 | 2057-11-07 19:53 | 2059-01-30 08:55 | 2060-04-22 21:57 | 2061-07-15 10:58 | 2062-10-07 | 2063-12-29 13:02 | 2065-03-22 02:03 | 2066-06-13 15:05 | 2067-09-05 04:07 | 2068-11-26 17:09 | 2070-02-18 06:10 | 2071-05-12 19:12 | 2072-08-03 08:14 | 2073-10-25 21:15 | 2075-01-17 10:17 | 2076-04-09 23:19 | 2077-07-02 12:21 | 2078-09-24 01:22 | 2079-12-16 14:24 | 2081-03-09 03:26 | 2082-05-31 16:27 | 2083-08-23 05:29 | 2084-11-13 18:31 | 2086-02-05 07:33 | 2087-04-29 20:34 | 2088-07-21 09:36 | 2089-10-12 22:38 | 2091-01-04 11:39 | 2092-03-28 00:41 | 2093-06-19 13:43 | 2094-09-11 02:45 | 2095-12-03 15:46 | 2097-02-24 04:48 | 2098-05-18 17:50 | 2099-08-10 06:51 | 2100-11-01 19:53 | 2102-01-24 08:55 | 2103-04-17 21:57 | 2104-07-09 10:58 | 2105-10-01 | 2106-12-23 13:02 | 2108-03-16 02:03 | 2109-06-07 15:05 | 2110-08-30 04:07 | 2111-11-21 17:09 | 2113-02-12 06:10 | 2114-05-06 19:12 | 2115-07-29 08:14 | 2116-10-19 21:15 | 2118-01-11 10:17 | 2119-04-04 23:19 | 2120-06-26 12:21 | 2121-09-18 01:22 | 2122-12-10 14:24 | 2124-03-03 03:26 | 2125-05-25 16:27 | 2126-08-17 05:29 | 2127-11-08 18:31 | 2129-01-30 07:33 | 2130-04-23 20:34 | 2131-07-16 09:36 | 2132-10-06 22:38 | 2133-12-29 11:39 | 2135-03-23 00:41 | 2136-06-13 13:43 | 2137-09-05 02:45 | 2138-11-27 15:46 | 2140-02-19 04:48 | 2141-05-12 17:50 | 2142-08-04 06:51 | 2143-10-26 19:53 | 2145-01-17 08:55 | 2146-04-10 21:57 | 2147-07-03 10:58 | 2148-09-24 | 2149-12-16 13:02 | 2151-03-10 02:03 | 2152-05-31 15:05 | 2153-08-23 04:07 | 2154-11-14 17:09 | 2156-02-06 06:10 | 2157-04-29 19:12 | 2158-07-22 08:14 | 2159-10-13 21:15 | 2161-01-04 10:17 | 2162-03-28 23:19 | 2163-06-20 12:21 | 2164-09-11 01:22 | 2165-12-03 14:24 | 2167-02-25 03:26 | 2168-05-18 16:27 | 2169-08-10 05:29 | 2170-11-01 18:31 | 2172-01-24 07:33 | 2173-04-16 20:34 | 2174-07-09 09:36 | 2175-09-30 22:38 | 2176-12-22 11:39 | 2178-03-16 00:41 | 2179-06-07 13:43 | 2180-08-29 02:45 | 2181-11-20 15:46 | 2183-02-12 04:48 | 2184-05-05 17:50 | 2185-07-28 06:51 | 2186-10-19 19:53 | 2188-01-11 08:55