## Variables
Windows 7 End of Support | 2019-10-31
Starting Date | 2018-01-15
Projections
Starting Windows 7 Count | 33050
Project Timeframe (Weeks) | 93
Projected Pace | 355.3763
Win7 25% | 24787.5
Win7 50% | 16525
Win7 75% | 8262.5
Win7 100% | 0

## Worksheet
Year | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020
Month | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Oct | Nov | Nov | Nov | Nov | Dec | Dec | Dec | Dec | Dec | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug
Day | 2018-01-15 | 2018-01-22 | 2018-01-26 | 2018-02-02 | 2018-02-09 | 2018-02-16 | 2018-02-23 | 2018-03-02 | 2018-03-08 | 2018-03-15 | 2018-03-22 | 2018-03-29 | 2018-04-05 | 2018-04-12 | 2018-04-19 | 2018-04-27 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 | 2019-04-01 | 2019-04-08 | 2019-04-15 | 2019-04-22 | 2019-04-29 | 2019-05-06 | 2019-05-13 | 2019-05-20 | 2019-05-27 | 2019-06-03 | 2019-06-10 | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02 | 2019-09-09 | 2019-09-16 | 2019-09-23 | 2019-09-30 | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31
Remaining Weeks | 93 | 92 | 91 | 90 | 89 | 88 | 87 | 86 | 86 | 85 | 84 | 83 | 82 | 81 | 80 | 78 | 77 | 76 | 75 | 74 | 73 | 72 | 71 | 70 | 69 | 68 | 67 | 66 | 65 | 64 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 55 | 54 | 53 | 52 | 51 | 50 | 49 | 48 | 47 | 46 | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 37 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
Remaining Months | 21 | 21 | 21 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 18 | 18 | 18 | 18 | 17 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 11 | 11 | 11 | 11 | 10 | 10 | 10 | 10 | 10 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -2 | -2 | -2 | -2 | -2 | -3 | -3 | -3 | -3 | -4 | -4 | -4 | -4 | -5 | -5 | -5 | -5 | -5 | -6 | -6 | -6 | -6 | -7 | -7 | -7 | -7 | -8 | -8 | -8 | -8 | -8 | -9 | -9 | -9 | -9 | -10 | -10 | -10 | -10 | -10
Actual Machine Counts
Windows 7 | 33050 | 32888 | 32713 | 32596 | 32548 | 32468 | 32116 | 31977 | 31919 | 32218 | 31754 | 31603 | 31300 | 30679 | 30748 | 28172 | 27457 | 27457 | 23144 | 23144 | 25336 | 24916 | 24642 | 24233 | 23698 | 23188 | 22795 | 22561 | 22105 | 21720 | 21147 | 20679 | 20114 | 19591 | 19591 | 18937 | 18673 | 18308 | 18018 | 17675 | 17277 | 16876 | 16557 | 16099 | 15714 | 15381 | 14982 | 14775 | 14433 | 14098 | 13447 | 12844 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926 | 12926
Windows 10 | 1855 | 1975 | 2090 | 2106 | 2439 | 2685 | 3044 | 3386 | 3367 | 4668 | 5049 | 5577 | 5964 | 6494 | 7089 | 6896 | 7369 | 7369 | 7124 | 7124 | 8715 | 9266 | 10144 | 10760 | 11267 | 11389 | 11633 | 12319 | 12704 | 13468 | 14119 | 14827 | 15474 | 15944 | 15944 | 16776 | 17347 | 17723 | 17962 | 18155 | 18406 | 18757 | 19017 | 19419 | 19914 | 19950 | 20298 | 20770 | 20959 | 21297 | 21321 | 20976 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994 | 21994
Weekly Change in W7 |  | -162 | -175 | -117 | -48 | -80 | -352 | -139 | -58 | 299 | -464 | -151 | -303 | -621 | 69 | -2576 | -715 | 0 | -4313 | 0 | 2192 | -420 | -274 | -409 | -535 | -510 | -393 | -234 | -456 | -385 | -573 | -468 | -565 | -523 | 0 | -654 | -264 | -365 | -290 | -343 | -398 | -401 | -319 | -458 | -385 | -333 | -399 | -207 | -342 | -335 | -651 | -603 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Weekly Change in W10 |  | 120 | 115 | 16 | 333 | 246 | 359 | 342 | -19 | 1301 | 381 | 528 | 387 | 530 | 595 | -193 | 473 | 0 | -245 | 0 | 1591 | 551 | 878 | 616 | 507 | 122 | 244 | 686 | 385 | 764 | 651 | 708 | 647 | 470 | 0 | 832 | 571 | 376 | 239 | 193 | 251 | 351 | 260 | 402 | 495 | 36 | 348 | 472 | 189 | 338 | 24 | -345 | 1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Running Changes in W7 | 0 | -162 | -337 | -454 | -502 | -582 | -934 | -1073 | -1131 | -832 | -1296 | -1447 | -1750 | -2371 | -2302 | -4878 | -5593 | -5593 | -9906 | -9906 | -7714 | -8134 | -8408 | -8817 | -9352 | -9862 | -10255 | -10489 | -10945 | -11330 | -11903 | -12371 | -12936 | -13459 | -13459 | -14113 | -14377 | -14742 | -15032 | -15375 | -15773 | -16174 | -16493 | -16951 | -17336 | -17669 | -18068 | -18275 | -18617 | -18952 | -19603 | -20206 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124 | -20124
Running Changes in W10 | 0 | 120 | 235 | 251 | 584 | 830 | 1189 | 1531 | 1512 | 2813 | 3194 | 3722 | 4109 | 4639 | 5234 | 5041 | 5514 | 5514 | 5269 | 5269 | 6860 | 7411 | 8289 | 8905 | 9412 | 9534 | 9778 | 10464 | 10849 | 11613 | 12264 | 12972 | 13619 | 14089 | 14089 | 14921 | 15492 | 15868 | 16107 | 16300 | 16551 | 16902 | 17162 | 17564 | 18059 | 18095 | 18443 | 18915 | 19104 | 19442 | 19466 | 19121 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139 | 20139
Average Weekly Change in W7 |  | -162 | -337 | -227 | -167.3333 | -145.5 | -186.8 | -178.8333 | -161.5714 | -104 | -144 | -144.7 | -159.0909 | -197.5833 | -177.0769 | -348.4286 | -349.5625 | -329 | -550.3333 | -521.3684 | -385.7 | -387.3333 | -382.1818 | -383.3478 | -389.6667 | -394.48 | -394.4231 | -388.4815 | -390.8929 | -390.6897 | -396.7667 | -399.0645 | -404.25 | -407.8485 | -395.8529 | -403.2286 | -399.3611 | -398.4324 | -395.5789 | -394.2308 | -394.325 | -394.4878 | -392.6905 | -394.2093 | -394 | -392.6444 | -392.7826 | -388.8298 | -387.8542 | -386.7755 | -392.06 | -396.1961 | -387 | -379.6981 | -372.6667 | -365.8909 | -359.3571 | -353.0526 | -346.9655 | -341.0847 | -335.4 | -329.9016 | -324.5806 | -319.4286 | -314.4375 | -309.6 | -304.9091 | -300.3582 | -295.9412 | -291.6522 | -287.4857 | -283.4366 | -279.5 | -275.6712 | -271.9459 | -268.32 | -264.7895 | -261.3506 | -258 | -254.7342 | -251.55 | -248.4444 | -245.4146 | -242.4578 | -239.5714 | -236.7529 | -234 | -231.3103 | -228.6818 | -226.1124 | -223.6 | -221.1429 | -218.7391 | -216.3871 | -214.0851 | -211.8316 | -209.625 | -207.4639 | -205.3469 | -203.2727 | -201.24 | -199.2475 | -197.2941 | -195.3786 | -193.5 | -191.6571 | -189.8491 | -188.0748 | -186.3333 | -184.6239 | -182.9455 | -181.2973 | -179.6786 | -178.0885 | -176.5263 | -174.9913 | -173.4828 | -172 | -170.5424 | -169.1092 | -167.7 | -166.314 | -164.9508 | -163.6098 | -162.2903 | -160.992 | -159.7143 | -158.4567 | -157.2188 | -156 | -154.8 | -153.6183 | -152.4545 | -151.3083 | -150.1791 | -149.0667 | -147.9706 | -146.8905
Average Weekly Change in W10 |  | 120 | 235 | 125.5 | 194.6667 | 207.5 | 237.8 | 255.1667 | 216 | 351.625 | 354.8889 | 372.2 | 373.5455 | 386.5833 | 402.6154 | 360.0714 | 344.625 | 324.3529 | 292.7222 | 277.3158 | 343 | 352.9048 | 376.7727 | 387.1739 | 392.1667 | 381.36 | 376.0769 | 387.5556 | 387.4643 | 400.4483 | 408.8 | 418.4516 | 425.5938 | 426.9394 | 414.3824 | 426.3143 | 430.3333 | 428.8649 | 423.8684 | 417.9487 | 413.775 | 412.2439 | 408.619 | 408.4651 | 410.4318 | 402.1111 | 400.9348 | 402.4468 | 398 | 396.7755 | 389.32 | 374.9216 | 387.2885 | 379.9811 | 372.9444 | 366.1636 | 359.625 | 353.3158 | 347.2241 | 341.339 | 335.65 | 330.1475 | 324.8226 | 319.6667 | 314.6719 | 309.8308 | 305.1364 | 300.5821 | 296.1618 | 291.8696 | 287.7 | 283.6479 | 279.7083 | 275.8767 | 272.1486 | 268.52 | 264.9868 | 261.5455 | 258.1923 | 254.9241 | 251.7375 | 248.6296 | 245.5976 | 242.6386 | 239.75 | 236.9294 | 234.1744 | 231.4828 | 228.8523 | 226.2809 | 223.7667 | 221.3077 | 218.9022 | 216.5484 | 214.2447 | 211.9895 | 209.7812 | 207.6186 | 205.5 | 203.4242 | 201.39 | 199.396 | 197.4412 | 195.5243 | 193.6442 | 191.8 | 189.9906 | 188.215 | 186.4722 | 184.7615 | 183.0818 | 181.4324 | 179.8125 | 178.2212 | 176.6579 | 175.1217 | 173.6121 | 172.1282 | 170.6695 | 169.2353 | 167.825 | 166.438 | 165.0738 | 163.7317 | 162.4113 | 161.112 | 159.8333 | 158.5748 | 157.3359 | 156.1163 | 154.9154 | 153.7328 | 152.5682 | 151.4211 | 150.291 | 149.1778 | 148.0809 | 147
Migration Progress [Percentage Complete]
Windows 7 Reduction (Project Progress) | 0% | 0.4902% | 1.02% | 1.374% | 1.519% | 1.761% | 2.826% | 3.247% | 3.422% | 2.517% | 3.921% | 4.378% | 5.295% | 7.174% | 6.965% | 14.76% | 16.92% | 16.92% | 29.97% | 29.97% | 23.34% | 24.61% | 25.44% | 26.68% | 28.3% | 29.84% | 31.03% | 31.74% | 33.12% | 34.28% | 36.02% | 37.43% | 39.14% | 40.72% | 40.72% | 42.7% | 43.5% | 44.61% | 45.48% | 46.52% | 47.72% | 48.94% | 49.9% | 51.29% | 52.45% | 53.46% | 54.67% | 55.3% | 56.33% | 57.34% | 59.31% | 61.14% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89%
Total Population (Windows 7 & 10) | 34905 | 34863 | 34803 | 34702 | 34987 | 35153 | 35160 | 35363 | 35286 | 36886 | 36803 | 37180 | 37264 | 37173 | 37837 | 35068 | 34826 | 34826 | 30268 | 30268 | 34051 | 34182 | 34786 | 34993 | 34965 | 34577 | 34428 | 34880 | 34809 | 35188 | 35266 | 35506 | 35588 | 35535 | 35535 | 35713 | 36020 | 36031 | 35980 | 35830 | 35683 | 35633 | 35574 | 35518 | 35628 | 35331 | 35280 | 35545 | 35392 | 35395 | 34768 | 33820 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920 | 34920
Windows 10 Percentage of Population | 5.314% | 5.665% | 6.005% | 6.069% | 6.971% | 7.638% | 8.658% | 9.575% | 9.542% | 12.66% | 13.72% | 15% | 16% | 17.47% | 18.74% | 19.66% | 21.16% | 21.16% | 23.54% | 23.54% | 25.59% | 27.11% | 29.16% | 30.75% | 32.22% | 32.94% | 33.79% | 35.32% | 36.5% | 38.27% | 40.04% | 41.76% | 43.48% | 44.87% | 44.87% | 46.97% | 48.16% | 49.19% | 49.92% | 50.67% | 51.58% | 52.64% | 53.46% | 54.67% | 55.89% | 56.47% | 57.53% | 58.43% | 59.22% | 60.17% | 61.32% | 62.02% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98% | 62.98%
Migration Progress
Projected Windows 7 Counts | 33050 | 32694.6237 | 32339.2473 | 31983.871 | 31628.4946 | 31273.1183 | 30917.7419 | 30562.3656 | 30206.9892 | 29851.6129 | 29496.2366 | 29140.8602 | 28785.4839 | 28430.1075 | 28074.7312 | 27719.3548 | 27363.9785 | 27008.6022 | 26653.2258 | 26297.8495 | 25942.4731 | 25587.0968 | 25231.7204 | 24876.3441 | 24520.9677 | 24165.5914 | 23810.2151 | 23454.8387 | 23099.4624 | 22744.086 | 22388.7097 | 22033.3333 | 21677.957 | 21322.5806 | 20967.2043 | 20611.828 | 20256.4516 | 19901.0753 | 19545.6989 | 19190.3226 | 18834.9462 | 18479.5699 | 18124.1935 | 17768.8172 | 17413.4409 | 17058.0645 | 16702.6882 | 16347.3118 | 15991.9355 | 15636.5591 | 15281.1828 | 14925.8065 | 14570.4301 | 14215.0538 | 13859.6774 | 13504.3011 | 13148.9247 | 12793.5484 | 12438.172 | 12082.7957 | 11727.4194 | 11372.043 | 11016.6667 | 10661.2903 | 10305.914 | 9950.5376 | 9595.1613 | 9239.7849 | 8884.4086 | 8529.0323 | 8173.6559 | 7818.2796 | 7462.9032 | 7107.5269 | 6752.1505 | 6396.7742 | 6041.3978 | 5686.0215 | 5330.6452 | 4975.2688 | 4619.8925 | 4264.5161 | 3909.1398 | 3553.7634 | 3198.3871 | 2843.0108 | 2487.6344 | 2132.2581 | 1776.8817 | 1421.5054 | 1066.129 | 710.7527 | 355.3763 | 4.7635e-11 | -355.3763 | -710.7527 | -1066.129 | -1421.5054 | -1776.8817 | -2132.2581 | -2487.6344 | -2843.0108 | -3198.3871 | -3553.7634 | -3909.1398 | -4264.5161 | -4619.8925 | -4975.2688 | -5330.6452 | -5686.0215 | -6041.3978 | -6396.7742 | -6752.1505 | -7107.5269 | -7462.9032 | -7818.2796 | -8173.6559 | -8529.0323 | -8884.4086 | -9239.7849 | -9595.1613 | -9950.5376 | -10305.914 | -10661.2903 | -11016.6667 | -11372.043 | -11727.4194 | -12082.7957 | -12438.172 | -12793.5484 | -13148.9247 | -13504.3011 | -13859.6774 | -14215.0538 | -14570.4301 | -14925.8065 | -15281.1828 | -15636.5591
Running Comparison | 0 | -193.3763 | -373.7527 | -612.129 | -919.5054 | -1194.8817 | -1198.2581 | -1414.6344 | -1712.0108 | -2366.3871 | -2257.7634 | -2462.1398 | -2514.5161 | -2248.8925 | -2673.2688 | -452.6452 | -93.0215 | -448.3978 | 3509.2258 | 3153.8495 | 606.4731 | 671.0968 | 589.7204 | 643.3441 | 822.9677 | 977.5914 | 1015.2151 | 893.8387 | 994.4624 | 1024.086 | 1241.7097 | 1354.3333 | 1563.957 | 1731.5806 | 1376.2043 | 1674.828 | 1583.4516 | 1593.0753 | 1527.6989 | 1515.3226 | 1557.9462 | 1603.5699 | 1567.1935 | 1669.8172 | 1699.4409 | 1677.0645 | 1720.6882 | 1572.3118 | 1558.9355 | 1538.5591 | 1834.1828 | 2081.8065 | 1644.4301 | 1289.0538 | 933.6774 | 578.3011 | 222.9247 | -132.4516 | -487.828 | -843.2043 | -1198.5806 | -1553.957 | -1909.3333 | -2264.7097 | -2620.086 | -2975.4624 | -3330.8387 | -3686.2151 | -4041.5914 | -4396.9677 | -4752.3441 | -5107.7204 | -5463.0968 | -5818.4731 | -6173.8495 | -6529.2258 | -6884.6022 | -7239.9785 | -7595.3548 | -7950.7312 | -8306.1075 | -8661.4839 | -9016.8602 | -9372.2366 | -9727.6129 | -10082.9892 | -10438.3656 | -10793.7419 | -11149.1183 | -11504.4946 | -11859.871 | -12215.2473 | -12570.6237 | -12926 | -13281.3763 | -13636.7527 | -13992.129 | -14347.5054 | -14702.8817 | -15058.2581 | -15413.6344 | -15769.0108 | -16124.3871 | -16479.7634 | -16835.1398 | -17190.5161 | -17545.8925 | -17901.2688 | -18256.6452 | -18612.0215 | -18967.3978 | -19322.7742 | -19678.1505 | -20033.5269 | -20388.9032 | -20744.2796 | -21099.6559 | -21455.0323 | -21810.4086 | -22165.7849 | -22521.1613 | -22876.5376 | -23231.914 | -23587.2903 | -23942.6667 | -24298.043 | -24653.4194 | -25008.7957 | -25364.172 | -25719.5484 | -26074.9247 | -26430.3011 | -26785.6774 | -27141.0538 | -27496.4301 | -27851.8065 | -28207.1828 | -28562.5591
Weeks into the Project | 0 | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137
Ahead/Behind Schedule | 0 | -0.54415 | -1.0517 | -1.7225 | -2.5874 | -3.3623 | -3.3718 | -3.9807 | -4.8175 | -6.6588 | -6.3532 | -6.9283 | -7.0756 | -6.3282 | -7.5224 | -1.2737 | -0.26175 | -1.2618 | 9.8747 | 8.8747 | 1.7066 | 1.8884 | 1.6594 | 1.8103 | 2.3158 | 2.7509 | 2.8567 | 2.5152 | 2.7983 | 2.8817 | 3.4941 | 3.811 | 4.4008 | 4.8725 | 3.8725 | 4.7128 | 4.4557 | 4.4828 | 4.2988 | 4.264 | 4.3839 | 4.5123 | 4.41 | 4.6987 | 4.7821 | 4.7191 | 4.8419 | 4.4244 | 4.3867 | 4.3294 | 5.1612 | 5.858 | 4.6273 | 3.6273 | 2.6273 | 1.6273 | 0.62729 | -0.37271 | -1.3727 | -2.3727 | -3.3727 | -4.3727 | -5.3727 | -6.3727 | -7.3727 | -8.3727 | -9.3727 | -10.3727 | -11.3727 | -12.3727 | -13.3727 | -14.3727 | -15.3727 | -16.3727 | -17.3727 | -18.3727 | -19.3727 | -20.3727 | -21.3727 | -22.3727 | -23.3727 | -24.3727 | -25.3727 | -26.3727 | -27.3727 | -28.3727 | -29.3727 | -30.3727 | -31.3727 | -32.3727 | -33.3727 | -34.3727 | -35.3727 | -36.3727 | -37.3727 | -38.3727 | -39.3727 | -40.3727 | -41.3727 | -42.3727 | -43.3727 | -44.3727 | -45.3727 | -46.3727 | -47.3727 | -48.3727 | -49.3727 | -50.3727 | -51.3727 | -52.3727 | -53.3727 | -54.3727 | -55.3727 | -56.3727 | -57.3727 | -58.3727 | -59.3727 | -60.3727 | -61.3727 | -62.3727 | -63.3727 | -64.3727 | -65.3727 | -66.3727 | -67.3727 | -68.3727 | -69.3727 | -70.3727 | -71.3727 | -72.3727 | -73.3727 | -74.3727 | -75.3727 | -76.3727 | -77.3727 | -78.3727 | -79.3727 | -80.3727
Forecasts Based on Actual Machine Counts
Monthly Pace Required | 1573.8095 | 1566.0952 | 1557.7619 | 1629.8 | 1627.4 | 1623.4 | 1605.8 | 1683 | 1679.9474 | 1695.6842 | 1671.2632 | 1663.3158 | 1738.8889 | 1704.3889 | 1708.2222 | 1565.1111 | 1615.1176 | 1615.1176 | 1361.4118 | 1361.4118 | 1583.5 | 1557.25 | 1540.125 | 1514.5625 | 1579.8667 | 1545.8667 | 1519.6667 | 1504.0667 | 1473.6667 | 1551.4286 | 1510.5 | 1477.0714 | 1436.7143 | 1507 | 1507 | 1456.6923 | 1436.3846 | 1525.6667 | 1501.5 | 1472.9167 | 1439.75 | 1406.3333 | 1505.1818 | 1463.5455 | 1428.5455 | 1398.2727 | 1498.2 | 1477.5 | 1443.3 | 1409.8 | 1344.7 | 1427.1111 | 1436.2222 | 1436.2222 | 1436.2222 | 1615.75 | 1615.75 | 1615.75 | 1615.75 | 1846.5714 | 1846.5714 | 1846.5714 | 1846.5714 | 2154.3333 | 2154.3333 | 2154.3333 | 2154.3333 | 2154.3333 | 2585.2 | 2585.2 | 2585.2 | 2585.2 | 3231.5 | 3231.5 | 3231.5 | 3231.5 | 4308.6667 | 4308.6667 | 4308.6667 | 4308.6667 | 4308.6667 | 6463 | 6463 | 6463 | 6463 | 12926 | 12926 | 12926 | 12926 | 12926 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -12926 | -12926 | -12926 | -12926 | -6463 | -6463 | -6463 | -6463 | -6463 | -4308.6667 | -4308.6667 | -4308.6667 | -4308.6667 | -3231.5 | -3231.5 | -3231.5 | -3231.5 | -2585.2 | -2585.2 | -2585.2 | -2585.2 | -2585.2 | -2154.3333 | -2154.3333 | -2154.3333 | -2154.3333 | -1846.5714 | -1846.5714 | -1846.5714 | -1846.5714 | -1615.75 | -1615.75 | -1615.75 | -1615.75 | -1615.75 | -1436.2222 | -1436.2222 | -1436.2222 | -1436.2222 | -1292.6 | -1292.6 | -1292.6 | -1292.6 | -1292.6
Weekly Pace Required | 355.3763 | 357.4783 | 359.4835 | 362.1778 | 365.7079 | 368.9545 | 369.1494 | 371.8256 | 371.1512 | 379.0353 | 378.0238 | 380.759 | 381.7073 | 378.7531 | 384.35 | 361.1795 | 356.5844 | 361.2763 | 308.5867 | 312.7568 | 347.0685 | 346.0556 | 347.0704 | 346.1857 | 343.4493 | 341 | 340.2239 | 341.8333 | 340.0769 | 339.375 | 335.6667 | 333.5323 | 329.7377 | 326.5167 | 332.0508 | 326.5 | 327.5965 | 326.9286 | 327.6 | 327.3148 | 325.9811 | 324.5385 | 324.6471 | 321.98 | 320.6939 | 320.4375 | 318.766 | 321.1957 | 320.7333 | 320.4091 | 312.7209 | 305.8095 | 315.2683 | 323.15 | 331.4359 | 340.1579 | 349.3514 | 359.0556 | 369.3143 | 380.1765 | 391.697 | 403.9375 | 416.9677 | 430.8667 | 445.7241 | 461.6429 | 478.7407 | 497.1538 | 517.04 | 538.5833 | 562 | 587.5455 | 615.5238 | 646.3 | 680.3158 | 718.1111 | 760.3529 | 807.875 | 861.7333 | 923.2857 | 994.3077 | 1077.1667 | 1175.0909 | 1292.6 | 1436.2222 | 1615.75 | 1846.5714 | 2154.3333 | 2585.2 | 3231.5 | 4308.6667 | 6463 | 12926 | #DIV/0! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
Percentage Complete
Percentage Complete (Win7) | 0% | 0.4902% | 1.02% | 1.374% | 1.519% | 1.761% | 2.826% | 3.247% | 3.422% | 2.517% | 3.921% | 4.378% | 5.295% | 7.174% | 6.965% | 14.76% | 16.92% | 16.92% | 29.97% | 29.97% | 23.34% | 24.61% | 25.44% | 26.68% | 28.3% | 29.84% | 31.03% | 31.74% | 33.12% | 34.28% | 36.02% | 37.43% | 39.14% | 40.72% | 40.72% | 42.7% | 43.5% | 44.61% | 45.48% | 46.52% | 47.72% | 48.94% | 49.9% | 51.29% | 52.45% | 53.46% | 54.67% | 55.3% | 56.33% | 57.34% | 59.31% | 61.14% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89% | 60.89%
Projected Target Date for 25% Complete |  | 2019-01-07 00:31 | 2018-07-09 14:59 | 2018-09-30 18:59 | 2018-12-30 15:25 | 2019-02-20 12:12 | 2018-11-24 14:57 | 2018-12-08 09:59 | 2019-01-10 23:15 | 2019-07-28 03:07 | 2019-02-23 15:35 | 2019-02-21 16:57 | 2019-01-16 13:12 | 2018-11-06 17:23 | 2018-12-10 14:58 | 2018-07-03 23:53 | 2018-06-29 10:58 | 2018-07-09 19:09 |  |  | 2018-06-13 22:55 | 2018-06-13 07:44
Projected Target Date for 50% Complete |  | 2019-12-30 01:02 | 2018-12-28 05:59 | 2019-06-12 13:57 | 2019-12-11 06:50 | 2020-03-24 00:25 | 2019-09-30 05:53 | 2019-10-27 19:57 | 2020-01-03 22:30 | 2021-02-03 06:14 | 2020-03-31 07:10 | 2020-03-27 09:54 | 2020-01-15 02:24 | 2019-08-26 10:47 | 2019-11-02 05:56 | 2018-12-16 23:46 | 2018-12-11 21:56 | 2019-01-01 14:18 | 2018-08-13 04:35 | 2018-08-24 20:50 | 2018-11-10 21:49 | 2018-11-09 15:28 | 2018-11-13 16:05 | 2018-11-12 17:59 | 2018-11-07 20:33 | 2018-11-04 05:37 | 2018-11-04 06:38 | 2018-11-08 18:17 | 2018-11-06 22:12 | 2018-11-07 01:54 | 2018-11-02 13:04 | 2018-10-31 20:46 | 2018-10-28 03:32 | 2018-10-25 14:56 | 2018-11-03 05:13 | 2018-10-28 20:56 | 2018-10-31 15:36 | 2018-11-01 07:48 | 2018-11-03 10:04 | 2018-11-04 10:04 | 2018-11-04 08:23 | 2018-11-04 05:29 | 2018-11-05 13:41
Projected Target Date for 75% Complete |  | 2020-12-21 01:33 | 2019-06-17 20:58 | 2020-02-22 08:56 | 2020-11-20 22:15 | 2021-04-25 12:37 | 2020-08-04 20:50 | 2020-09-15 05:56 | 2020-12-26 21:44 | 2022-08-13 09:21 | 2021-05-06 22:45 | 2021-05-01 02:51 | 2021-01-12 15:36 | 2020-06-14 04:10 | 2020-09-23 20:54 | 2019-05-31 23:40 | 2019-05-26 08:53 | 2019-06-26 09:27 | 2018-11-26 06:52 | 2018-12-13 19:15 | 2019-04-09 20:44 | 2019-04-07 23:12 | 2019-04-14 00:07 | 2019-04-12 14:59 | 2019-04-05 06:50 | 2019-03-30 20:26 | 2019-03-30 21:57 | 2019-04-06 15:26 | 2019-04-03 21:18 | 2019-04-04 02:51 | 2019-03-28 07:35 | 2019-03-25 19:09 | 2019-03-20 05:18 | 2019-03-16 10:25 | 2019-03-29 07:49 | 2019-03-21 07:24 | 2019-03-25 11:24 | 2019-03-26 11:43 | 2019-03-29 15:06 | 2019-03-31 03:06 | 2019-03-31 00:35 | 2019-03-30 20:13 | 2019-04-01 20:32 | 2019-03-31 03:41 | 2019-03-31 09:17 | 2019-04-01 21:47 | 2019-04-01 18:03 | 2019-04-06 05:50 | 2019-04-07 08:46 | 2019-04-08 14:43 | 2019-04-02 13:35 | 2019-03-28 22:42 | 2019-04-08 08:28 | 2019-04-16 23:24 | 2019-04-25 14:20 | 2019-05-04 05:16 | 2019-05-12 20:12 | 2019-05-21 11:08 | 2019-05-30 02:03 | 2019-06-07 16:59 | 2019-06-16 07:55 | 2019-06-24 22:51 | 2019-07-03 13:47 | 2019-07-12 04:43 | 2019-07-20 19:39 | 2019-07-29 10:35 | 2019-08-07 01:31 | 2019-08-15 16:27 | 2019-08-24 07:23 | 2019-09-01 22:19 | 2019-09-10 13:14 | 2019-09-19 04:10 | 2019-09-27 19:06 | 2019-10-06 10:02 | 2019-10-15 00:58 | 2019-10-23 15:54 | 2019-11-01 06:50 | 2019-11-09 21:46 | 2019-11-18 12:42 | 2019-11-27 03:38 | 2019-12-05 18:34 | 2019-12-14 09:30 | 2019-12-23 00:26 | 2019-12-31 15:21 | 2020-01-09 06:17 | 2020-01-17 21:13 | 2020-01-26 12:09 | 2020-02-04 03:05 | 2020-02-12 18:01 | 2020-02-21 08:57 | 2020-02-29 23:53 | 2020-03-09 14:49 | 2020-03-18 05:45 | 2020-03-26 20:41 | 2020-04-04 11:37 | 2020-04-13 02:33 | 2020-04-21 17:28 | 2020-04-30 08:24 | 2020-05-08 23:20 | 2020-05-17 14:16 | 2020-05-26 05:12 | 2020-06-03 20:08 | 2020-06-12 11:04 | 2020-06-21 02:00 | 2020-06-29 16:56 | 2020-07-08 07:52 | 2020-07-16 22:48 | 2020-07-25 13:44 | 2020-08-03 04:39 | 2020-08-11 19:35 | 2020-08-20 10:31 | 2020-08-29 01:27 | 2020-09-06 16:23 | 2020-09-15 07:19 | 2020-09-23 22:15 | 2020-10-02 13:11 | 2020-10-11 04:07 | 2020-10-19 19:03 | 2020-10-28 09:59 | 2020-11-06 00:55 | 2020-11-14 15:51 | 2020-11-23 06:46 | 2020-12-01 21:42 | 2020-12-10 12:38 | 2020-12-19 03:34 | 2020-12-27 18:30 | 2021-01-05 09:26 | 2021-01-14 00:22 | 2021-01-22 15:18 | 2021-01-31 06:14 | 2021-02-08 21:10 | 2021-02-17 12:06 | 2021-02-26 03:02 | 2021-03-06 17:58 | 2021-03-15 08:53 | 2021-03-23 23:49 | 2021-04-01 14:45 | 2021-04-10 05:41
Projected Target Date for 100% Complete |  | 2021-12-13 02:04 | 2019-12-06 11:58 | 2020-11-03 03:55 | 2021-11-01 13:40 | 2022-05-28 00:49 | 2021-06-10 11:46 | 2021-08-04 15:54 | 2021-12-19 20:59 | 2024-02-20 12:28 | 2022-06-12 14:20 | 2022-06-04 19:48 | 2022-01-11 04:48 | 2021-04-02 21:34 | 2021-08-16 11:52 | 2019-11-13 23:33 | 2019-11-07 19:51 | 2019-12-19 04:36 | 2019-03-11 09:09 | 2019-04-03 17:40 | 2019-09-06 19:39 | 2019-09-04 06:56 | 2019-09-12 08:10 | 2019-09-10 11:58 | 2019-08-31 17:06 | 2019-08-24 11:14 | 2019-08-24 13:16 | 2019-09-02 12:34 | 2019-08-29 20:24 | 2019-08-30 03:48 | 2019-08-21 02:07 | 2019-08-17 17:32 | 2019-08-10 07:04 | 2019-08-05 05:53 | 2019-08-22 10:25 | 2019-08-11 17:51 | 2019-08-17 07:12 | 2019-08-18 15:37 | 2019-08-22 20:08 | 2019-08-24 20:08 | 2019-08-24 16:46 | 2019-08-24 10:58 | 2019-08-27 03:23 | 2019-08-24 20:54 | 2019-08-25 04:23 | 2019-08-27 05:02 | 2019-08-27 00:04 | 2019-09-01 23:46 | 2019-09-03 11:41 | 2019-09-05 03:37 | 2019-08-28 02:07 | 2019-08-21 22:16 | 2019-09-04 19:17 | 2019-09-16 07:12 | 2019-09-27 19:06 | 2019-10-09 07:01 | 2019-10-20 18:55 | 2019-11-01 06:50 | 2019-11-12 18:45 | 2019-11-24 06:39 | 2019-12-05 18:34 | 2019-12-17 06:28 | 2019-12-28 18:23 | 2020-01-09 06:17 | 2020-01-20 18:12 | 2020-02-01 06:07 | 2020-02-12 18:01 | 2020-02-24 05:56 | 2020-03-06 17:50 | 2020-03-18 05:45 | 2020-03-29 17:39 | 2020-04-10 05:34 | 2020-04-21 17:28 | 2020-05-03 05:23 | 2020-05-14 17:18 | 2020-05-26 05:12 | 2020-06-06 17:07 | 2020-06-18 05:01 | 2020-06-29 16:56 | 2020-07-11 04:50 | 2020-07-22 16:45 | 2020-08-03 04:39 | 2020-08-14 16:34 | 2020-08-26 04:29 | 2020-09-06 16:23 | 2020-09-18 04:18 | 2020-09-29 16:12 | 2020-10-11 04:07 | 2020-10-22 16:01 | 2020-11-03 03:56 | 2020-11-14 15:51 | 2020-11-26 03:45 | 2020-12-07 15:40 | 2020-12-19 03:34 | 2020-12-30 15:29 | 2021-01-11 03:23 | 2021-01-22 15:18 | 2021-02-03 03:12 | 2021-02-14 15:07 | 2021-02-26 03:02 | 2021-03-09 14:56 | 2021-03-21 02:51 | 2021-04-01 14:45 | 2021-04-13 02:40 | 2021-04-24 14:34 | 2021-05-06 02:29 | 2021-05-17 14:24 | 2021-05-29 02:18 | 2021-06-09 14:13 | 2021-06-21 02:07 | 2021-07-02 14:02 | 2021-07-14 01:56 | 2021-07-25 13:51 | 2021-08-06 01:45 | 2021-08-17 13:40 | 2021-08-29 01:35 | 2021-09-09 13:29 | 2021-09-21 01:24 | 2021-10-02 13:18 | 2021-10-14 01:13 | 2021-10-25 13:07 | 2021-11-06 01:02 | 2021-11-17 12:57 | 2021-11-29 00:51 | 2021-12-10 12:46 | 2021-12-22 00:40 | 2022-01-02 12:35 | 2022-01-14 00:29 | 2022-01-25 12:24 | 2022-02-06 00:18 | 2022-02-17 12:13 | 2022-03-01 00:08 | 2022-03-12 12:02 | 2022-03-23 23:57 | 2022-04-04 11:51 | 2022-04-15 23:46 | 2022-04-27 11:40 | 2022-05-08 23:35